## Read Me
CMMC Level 2 POA&M Template
Free download from Solas AI - solasai.net
What this is
A Plan of Action & Milestones (POA&M) tracker aligned to NIST SP 800-171 Rev 2 and the DoD Assessment Methodology. Use it to log every gap, assign an owner, set planned vs actual milestones, and compute a current SPRS score.
How to use it
1. Fill in the org metadata at the top of the POA&M Tracker sheet. 2. Add one row per finding. Pick Status and Risk Level from the dropdowns. 3. Enter the SPRS Point Value (1, 3, or 5) per the control's weight in the DoD Assessment Methodology. 4. Track planned and actual dates as remediation progresses. 5. The SPRS Summary sheet auto-totals deductions for any non-Closed row.
Column reference
POA&M ID: your internal tracking number (POA-001, POA-002...). Source: where the finding came from (self-assessment, C3PAO, internal audit, etc.). Control Family / Control ID: the NIST SP 800-171 Rev 2 family code and section (e.g., AC / 3.1.5). Status: Open, In Progress, Delayed, Pending Verification, Closed, or Risk Accepted. Closure Evidence: artifact reference proving remediation (ticket #, screenshot path, policy section).
About the author
Built by David Moline, a Department of Defense Information System Security Manager (ISSM), CISSP, and CISM. This template is the lightweight tracker component of the full Solas AI CMMC Level 2 Evidence Builder kit.
Need more than a tracker?
The full CMMC Level 2 Evidence Builder kit ($297) includes the System Security Plan template, implementation statements for all 110 controls, 14 policy templates (one per control family), evidence collection guidance, C3PAO readiness checklist, and the assessment-day playbook. Get it at: solasai.net/products/cmmc-evidence-builder
License
Free for any organization to use, internally and with clients. Do not resell as your own product.

## POA&M Tracker
CMMC Level 2 - Plan of Action & Milestones (POA&M)
Organization Name:
System / Boundary:
Prepared By:
Date Prepared:
Assessment Type: | Self-Assessment / C3PAO / Other
Document Version: | 1.0
POA&M ID | Date Identified | Source | Control Family | Control ID | Finding / Weakness | SPRS Point Value | Risk Level | Status | Owner | Resources Required | Planned Milestones | Planned Start | Planned Completion | Actual Start | Actual Completion | Closure Evidence | Notes
POA-001 | 2026-04-15 | Self-Assessment | IA | 3.5.3 | MFA not enforced for remote VPN access for two service accounts used by integration jobs. | 5 | High | In Progress | IT Lead - J. Smith | Identity provider config, ~6 hrs labor, no new spend | 1) Inventory affected accounts 2) Move jobs to FIDO2 hardware tokens 3) Disable password-only fallback | 2026-05-01 | 2026-06-15 | 2026-05-03 |  |  | Tracked under change request CHG-1042.
POA-002 | 2026-04-15 | Self-Assessment | AU | 3.3.8 | Audit logs on the file server are world-readable; any authenticated user can view them. | 5 | High | Open | SysAdmin - K. Patel | ACL change + Group Policy update, ~2 hrs labor | 1) Restrict log directory ACL to Auditors group 2) Validate via fresh non-admin session 3) Document baseline | 2026-05-10 | 2026-05-24
POA-003 | 2026-04-15 | Self-Assessment | MP | 3.8.3 | No documented media sanitization procedure for retired laptops containing CUI. | 3 | Moderate | Open | ISSO - D. Moline | Policy draft + 1x NIST 800-88 verification tool, ~$0 (existing tooling) | 1) Draft sanitization SOP 2) Train deskside support 3) Add chain-of-custody log to asset retirement workflow | 2026-06-01 | 2026-07-15

## SPRS Summary
SPRS Score Calculator
Per the DoD Assessment Methodology v1.2.1, scoring starts at 110 and each
open or partially implemented control deducts its SPRS point value (1, 3, or 5).
Maximum score: 110. Minimum: -203. Only fully implemented controls earn full credit.
This sheet auto-calculates the deduction from any rows in the POA&M Tracker
where Status is NOT 'Closed' and a SPRS Point Value (1/3/5) has been entered.
Starting Score | 110
Total Deductions (open + partial findings)
Current SPRS Score

## Control Reference
NIST SP 800-171 Rev 2 - 110 Security Requirements
Brief functional descriptors. Full control text is in NIST SP 800-171 Rev 2 (free at csrc.nist.gov/publications/detail/sp/800-171/rev-2/final).
Family | Family Name | Control ID | Brief Description
AC | Access Control | 3.1.1 | Limit system access to authorized users and devices
AC | Access Control | 3.1.2 | Limit system access to permitted transactions and functions
AC | Access Control | 3.1.3 | Control flow of CUI
AC | Access Control | 3.1.4 | Separate duties of individuals
AC | Access Control | 3.1.5 | Employ least privilege
AC | Access Control | 3.1.6 | Use non-privileged accounts for non-security functions
AC | Access Control | 3.1.7 | Prevent non-privileged users from executing privileged functions
AC | Access Control | 3.1.8 | Limit unsuccessful logon attempts
AC | Access Control | 3.1.9 | Provide privacy and security notices
AC | Access Control | 3.1.10 | Use session lock with pattern-hiding displays
AC | Access Control | 3.1.11 | Terminate user sessions after defined condition
AC | Access Control | 3.1.12 | Monitor and control remote access sessions
AC | Access Control | 3.1.13 | Use cryptography to protect remote access sessions
AC | Access Control | 3.1.14 | Route remote access via managed access control points
AC | Access Control | 3.1.15 | Authorize remote execution of privileged commands
AC | Access Control | 3.1.16 | Authorize wireless access prior to connection
AC | Access Control | 3.1.17 | Protect wireless access using authentication and encryption
AC | Access Control | 3.1.18 | Control connection of mobile devices
AC | Access Control | 3.1.19 | Encrypt CUI on mobile devices and platforms
AC | Access Control | 3.1.20 | Verify and control connections to external systems
AC | Access Control | 3.1.21 | Limit use of organizational portable storage on external systems
AC | Access Control | 3.1.22 | Control CUI posted to publicly accessible systems
AT | Awareness and Training | 3.2.1 | Ensure personnel are aware of security risks
AT | Awareness and Training | 3.2.2 | Train personnel to carry out assigned security duties
AT | Awareness and Training | 3.2.3 | Provide insider threat awareness training
AU | Audit and Accountability | 3.3.1 | Create and retain system audit logs
AU | Audit and Accountability | 3.3.2 | Ensure actions are traceable to individual users
AU | Audit and Accountability | 3.3.3 | Review and update logged events
AU | Audit and Accountability | 3.3.4 | Alert on audit logging process failure
AU | Audit and Accountability | 3.3.5 | Correlate audit review, analysis, and reporting processes
AU | Audit and Accountability | 3.3.6 | Provide audit reduction and report generation
AU | Audit and Accountability | 3.3.7 | Synchronize system clocks to an authoritative source
AU | Audit and Accountability | 3.3.8 | Protect audit information from unauthorized access
AU | Audit and Accountability | 3.3.9 | Limit management of audit logging to a subset of privileged users
CM | Configuration Management | 3.4.1 | Establish and maintain baseline configurations
CM | Configuration Management | 3.4.2 | Enforce security configuration settings
CM | Configuration Management | 3.4.3 | Track, review, approve, and log changes
CM | Configuration Management | 3.4.4 | Analyze security impact of changes
CM | Configuration Management | 3.4.5 | Define, document, approve, and enforce access restrictions for changes
CM | Configuration Management | 3.4.6 | Employ principle of least functionality
CM | Configuration Management | 3.4.7 | Restrict, disable, or prevent use of nonessential functions
CM | Configuration Management | 3.4.8 | Apply deny-by-exception (blacklist) or permit-by-exception (whitelist) policy
CM | Configuration Management | 3.4.9 | Control and monitor user-installed software
IA | Identification and Authentication | 3.5.1 | Identify users, processes, and devices
IA | Identification and Authentication | 3.5.2 | Authenticate identities before access
IA | Identification and Authentication | 3.5.3 | Use multi-factor authentication for privileged and remote access
IA | Identification and Authentication | 3.5.4 | Employ replay-resistant authentication for network access
IA | Identification and Authentication | 3.5.5 | Prevent reuse of identifiers for a defined period
IA | Identification and Authentication | 3.5.6 | Disable identifiers after a defined period of inactivity
IA | Identification and Authentication | 3.5.7 | Enforce minimum password complexity
IA | Identification and Authentication | 3.5.8 | Prohibit password reuse for a defined number of generations
IA | Identification and Authentication | 3.5.9 | Allow temporary password use with immediate change
IA | Identification and Authentication | 3.5.10 | Store and transmit only cryptographically-protected passwords
IA | Identification and Authentication | 3.5.11 | Obscure feedback of authentication information
IR | Incident Response | 3.6.1 | Establish an operational incident-handling capability
IR | Incident Response | 3.6.2 | Track, document, and report incidents
IR | Incident Response | 3.6.3 | Test the incident response capability
MA | Maintenance | 3.7.1 | Perform maintenance on organizational systems
MA | Maintenance | 3.7.2 | Provide controls on the tools, techniques, and personnel used for maintenance
MA | Maintenance | 3.7.3 | Sanitize equipment removed for off-site maintenance
MA | Maintenance | 3.7.4 | Check media containing diagnostic and test programs for malicious code
MA | Maintenance | 3.7.5 | Require multi-factor authentication for nonlocal maintenance sessions
MA | Maintenance | 3.7.6 | Supervise maintenance activities of personnel without required access
MP | Media Protection | 3.8.1 | Protect (physically control and securely store) CUI media
MP | Media Protection | 3.8.2 | Limit access to CUI on media to authorized users
MP | Media Protection | 3.8.3 | Sanitize or destroy media before disposal or reuse
MP | Media Protection | 3.8.4 | Mark media containing CUI with applicable distribution limitations
MP | Media Protection | 3.8.5 | Control access to CUI media and maintain accountability during transport
MP | Media Protection | 3.8.6 | Implement cryptographic mechanisms to protect CUI on transported media
MP | Media Protection | 3.8.7 | Control use of removable media on system components
MP | Media Protection | 3.8.8 | Prohibit use of portable storage devices with no identifiable owner
MP | Media Protection | 3.8.9 | Protect the confidentiality of backup CUI
PS | Personnel Security | 3.9.1 | Screen individuals prior to authorizing access to CUI
PS | Personnel Security | 3.9.2 | Ensure CUI and systems are protected during and after personnel actions
PE | Physical Protection | 3.10.1 | Limit physical access to organizational systems and equipment
PE | Physical Protection | 3.10.2 | Protect and monitor the physical facility and support infrastructure
PE | Physical Protection | 3.10.3 | Escort visitors and monitor visitor activity
PE | Physical Protection | 3.10.4 | Maintain audit logs of physical access
PE | Physical Protection | 3.10.5 | Control and manage physical access devices
PE | Physical Protection | 3.10.6 | Enforce safeguarding measures for CUI at alternate work sites
RA | Risk Assessment | 3.11.1 | Periodically assess risk to operations and CUI
RA | Risk Assessment | 3.11.2 | Scan for vulnerabilities periodically and when new vulnerabilities are identified
RA | Risk Assessment | 3.11.3 | Remediate vulnerabilities in accordance with risk assessments
CA | Security Assessment | 3.12.1 | Periodically assess security controls for effectiveness
CA | Security Assessment | 3.12.2 | Develop and implement plans of action to correct deficiencies
CA | Security Assessment | 3.12.3 | Monitor security controls on an ongoing basis
CA | Security Assessment | 3.12.4 | Develop, document, and periodically update System Security Plans
SC | System and Communications Protection | 3.13.1 | Monitor, control, and protect communications at boundaries
SC | System and Communications Protection | 3.13.2 | Employ architectural designs that promote effective security
SC | System and Communications Protection | 3.13.3 | Separate user functionality from system management functionality
SC | System and Communications Protection | 3.13.4 | Prevent unauthorized information transfer via shared resources
SC | System and Communications Protection | 3.13.5 | Implement subnetworks for publicly accessible system components
SC | System and Communications Protection | 3.13.6 | Deny network communications traffic by default, allow by exception
SC | System and Communications Protection | 3.13.7 | Prevent remote devices from simultaneously establishing non-remote connections (split tunneling)
SC | System and Communications Protection | 3.13.8 | Implement cryptographic mechanisms to prevent unauthorized disclosure of CUI in transit
SC | System and Communications Protection | 3.13.9 | Terminate network connections at end of session or after defined inactivity
SC | System and Communications Protection | 3.13.10 | Establish and manage cryptographic keys
SC | System and Communications Protection | 3.13.11 | Employ FIPS-validated cryptography to protect CUI
SC | System and Communications Protection | 3.13.12 | Prohibit remote activation of collaborative computing devices
SC | System and Communications Protection | 3.13.13 | Control and monitor use of mobile code
SC | System and Communications Protection | 3.13.14 | Control and monitor use of Voice over Internet Protocol
SC | System and Communications Protection | 3.13.15 | Protect authenticity of communications sessions
SC | System and Communications Protection | 3.13.16 | Protect confidentiality of CUI at rest
SI | System and Information Integrity | 3.14.1 | Identify, report, and correct system flaws in a timely manner
SI | System and Information Integrity | 3.14.2 | Provide protection from malicious code at designated locations
SI | System and Information Integrity | 3.14.3 | Monitor security alerts and advisories and take action in response
SI | System and Information Integrity | 3.14.4 | Update malicious code protection mechanisms when new releases are available
SI | System and Information Integrity | 3.14.5 | Perform periodic and real-time scans for malicious code
SI | System and Information Integrity | 3.14.6 | Monitor the system to detect attacks and indicators of potential attacks
SI | System and Information Integrity | 3.14.7 | Identify unauthorized use of organizational systems